## Gantt Chart
FLARE
Owner: | Max Schneeberger
Legend: | WP Duration
WT Duration
● = Deliverable
þ = Milestone
GM
WS
WP | WT | WT Title | March 2025 |  |  |  | April 2025 |  |  |  | May 2025 |  |  |  | June 2025
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
0 | Project Management
| 0.1 | implementation of the project management structure | bar: March 2025 W1 to March 2025 W3
| 0.2 | setting up project management documents | bar: March 2025 W2 to March 2025 W4
| 0.3 | reporting to stakeholders | April 2025 W1: GM ●; April 2025 W2: GM ●; May 2025 W2: GM ●; June 2025 W2: GM ●; June 2025 W3: GM ●; June 2025 W4: WS
1 | Project Initiation | bar: March 2025 W1 to April 2025 W4
| 1.1 | define project scope and objectives | bar: March 2025 W1 to March 2025 W2
| 1.2 | define stakeholders | bar: March 2025 W1 to March 2025 W3
| 1.3 | literature review | bar: March 2025 W4 to April 2025 W3
| 1.4 | data acquisition & cleaning | bar: April 2025 W2 to April 2025 W4
2 | Main Analysis Phase | bar: April 2025 W1 to May 2025 W2
| 2.1 | testing methods | bar: April 2025 W1 to April 2025 W3
| 2.2 | WUI extraction workflow | bar: April 2025 W3 to May 2025 W1
| 2.3 | wilfire risk mapping workflow | bar: April 2025 W3 to May 2025 W1
| 2.4 | integrating results of WT 2.2 & WT 2.3 | bar: April 2025 W4 to May 2025 W2
3 | Streamlining Outcomes | bar: May 2025 W1 to June 2025 W1
| 3.1 | validation of results | bar: May 2025 W1 to May 2025 W2
| 3.2 | interpreting results | bar: May 2025 W1 to May 2025 W2
| 3.3 | finalizing research paper | bar: May 2025 W2 to June 2025 W1
4 | Presentation of Outcomes | bar: June 2025 W1 to June 2025 W4
| 4.1 | designing poster | bar: June 2025 W1 to June 2025 W2
| 4.2 | getting feedback for poster | bar: June 2025 W3
| 4.4 | poster presentation | bar: June 2025 W4